PROJECT CHARTER

Most2baly Youth Summer Bootcamp

| Project Name | Most2baly Youth Summer Bootcamp |
| --- | --- |
| Project Sponsor | Most2baly Leadership Team |
| Project Manager | PM C1 team 2 - Hesham Mohamed - Ali Elgazzar - Doha Ahmed - Ahmed Zaki |
| Date | April 24, 2026 |
| Version | 1.0 |

1. Project Purpose and Justification

High school students (ages 15–18) are academically prepared but critically lack real-world professional skills. Upon entering university or their first internship, they consistently struggle with time management, professional communication, and structuring their work effectively.

Most2baly Youth will bridge this gap by delivering a focused, 4-week online summer bootcamp covering foundational professional skills. This initiative also strategically positions Most2baly to capture a younger demographic and build brand loyalty before students graduate high school.

If this project is not executed, students will continue entering university and workplaces underprepared — and Most2baly will miss a critical first-mover opportunity in the high school professional development space, ceding ground to competitors.

2. Measurable Objectives and Success Criteria

Objective 1: Student Enrollment

Enroll exactly 50 high school students in the pilot cohort before the bootcamp launch on July 24, 2026.

Success Criteria:

Enrollment platform confirms 50 registered and paid students by July 10, 2026 (2 weeks before launch).

Objective 2: Graduation Rate

Achieve a minimum 80% graduation rate — meaning at least 40 out of 50 enrolled students complete all 4 weeks of the bootcamp by August 21, 2026.

Success Criteria:

Learning Management System (LMS) completion data confirms ≥ 40 students have completed all modules and final deliverables.

Objective 3: Parent Satisfaction (NPS)

Achieve a Net Promoter Score (NPS) of +50 or higher from parents within 2 weeks of bootcamp completion.

Success Criteria:

Post-program parent survey (sent by August 28, 2026) returns an NPS of +50 or above, confirming parents found the program valuable enough to recommend.

3. High-Level Requirements

IN SCOPE — What We Will Deliver:

- 4-week, fully online summer bootcamp designed for high school students (ages 15–18)

- Curriculum covering three core modules: (1) Time Management, (2) Professional Communication, (3) Goal-Setting & Introductory Project Planning

- Targeted marketing campaign aimed at parents across social media and email channels

- Enroll exactly 50 students for pilot cohort

- Online platform hosting for all live sessions and recorded content (Zoom or LMS)

- 2 guest speaker sessions featuring young professionals coordinated by the Project Manager

- Develop engaging, age-appropriate content for students (15–18) and parent information pack

- Track attendance, engagement, and completion rates

OUT OF SCOPE — Explicitly Excluded (Scope Creep Prevention):

Technical skills training — NO coding, programming, or digital marketing content

University admissions counseling or academic tutoring of any kind

Internship placement, guarantees, or job referrals

In-person or hybrid sessions — online delivery only

4. High-Level Risks

Risk 1: Low Enrollment (HIGH IMPACT)

Failure to recruit 50 students before the launch date

Impact: Failure to meet financial viability

Mitigation: Launch a targeted parent-focused marketing campaign by May 15, 2026 — 10 weeks before the enrollment deadline. Track weekly enrollment numbers with a clear escalation plan if numbers fall behind.

Risk 2: Student Disengagement (MEDIUM IMPACT)

Teenagers participating in a 4-week online program over summer may lose motivation

Impact: Drop-in completion rate below 80%

Mitigation: Design interactive, gamified weekly challenges. Incorporate the 2 guest speaker sessions strategically in weeks 2 and 3 to re-energize students at critical drop-off points, gamification, short modules

Risk 3: Platform / Technical Failures (MEDIUM IMPACT)

Online hosting platform may experience downtime, audio/video issues, or compatibility problems during live sessions.

Impact: Poor user experience, dissatisfaction

Mitigation: Complete full platform testing 2 weeks before Go-Live (by July 10, 2026). Identify and document a backup platform. Provide students with a pre-bootcamp tech check session.

5. Summary Milestone Schedule

| Milestone | Target Date |
| --- | --- |
| Project Kickoff & Charter Approved | April 28, 2026 |
| Content Development & Curriculum Complete | April 30, 2026 |
| Marketing Campaign Launched (targeting parents) | May 15, 2026 |
| Platform Setup & Full Technical Testing | June 10, 2026 |
| Guest Speakers Confirmed & Briefed | June 20, 2026 |
| Enrollment Deadline (50 students confirmed) | July 10, 2026 |
| Bootcamp Go-Live / Week 1 Begins | July 24, 2026 |
| Bootcamp Completion / Week 4 Ends | August 21, 2026 |
| Parent NPS Survey Distributed | August 22, 2026 |
| Post-Project Review & Final Report | August 28, 2026 |

6. Summary Budget

Total Estimated Budget: $5,000 (HARD CAP — Sponsor Constraint)

| Cost Category | Estimated Cost |
| --- | --- |
| Parent-targeted marketing (social media ads, email campaigns) | $2,000 |
| Online platform hosting & technical setup | $2,000 |
| Curriculum materials, student resources & contingency | $1,000 |
| TOTAL | $5,000 |

7. Key Stakeholders

Sponsor:

Most2baly Leadership Team — Funding the project. Primary concern: on budget, on time, 50 students enrolled.

End Users / Customers:

- Students (ages 15–18): End-users who attend the bootcamp. Content must be engaging, practical, and relevant to their world.

- Parents: The actual buyers and decision-makers. They must see clear value to justify the enrollment fee.

Subject Matter Experts / Team Members:

- Guest Speaker #1 — Young professional (to be coordinated by PM)

- Guest Speaker #2 — Young professional (to be coordinated by PM)

- Content Designer — Responsible for building engaging curriculum materials

- Marketing team.

8. Project Manager Authority Level

Staffing Authority:

The Project Manager may assign tasks to designated team members but cannot hire external contractors or reallocate staff from other departments without explicit Sponsor approval.

Budget Approval Limit:

The Project Manager may approve individual project expenses up to $5000 without secondary Sponsor approval. Any expense above $5000 requires written Sponsor sign-off.

Schedule Flexibility:

The Project Manager may adjust internal milestone dates by up to 3 business days, provided the final Go-Live date of July 24, 2026 is not impacted.

9. Approvals

| Sponsor Name | Signature | Date |
| --- | --- | --- |
| Most2baly Leadership Team | Most2baly Youth | April 28, 2026 |

Most2baly Youth Summer Bootcamp  |  Project Charter v1.0  |  April 24, 2026