## 🏠 Dashboard Overview
🚀 MOST2BALY YOUTH BOOTCAMP ¦ PROJECT HEALTH DASHBOARD ¦ THE MID-TERM PERFORMANCE AUDIT
Project Manager: PM C1 team 2 ¦ 1.Hesham Mohamed ¦ 2.Ali Elgazzar ¦ 3.Doha Ahmed ¦ 4.Ahmed Zaki
Project Manager Performance Audit • Resource Leveling • EVM Analysis • Budget Control
SPI | CPI |  | BAC |  | EV
0.80 | 0.86 |  | $5,000 |  | $1,500
Schedule Performance Index | Cost Performance Index |  | Budget At Completion Total Project Budget |  | Earned Value (Week 6)
⚠️ Behind Schedule | ⚠️ Over Budget |  | ✅ Defined & Controlled |  | Work Completed Value
AC |  | PV |  | EAC
$1,750 |  | $1,875 |  | 5834
Actual Cost (Week 6) |  | Planned Value (Week 6) |  | Estimate at Completion
Total Spent So Far |  | Work Planned Value |  | If Trend Continues
📊 QUICK NAVIGATION — This workbook contains 4 professional sheets
📊 Sheet 2 |  | 💰 Sheet 3 |  | 📈 Sheet 4
Resource Utilization Matrix |  | Three-Envelope Budget |  | EVM Health Indices
Who is doing what • Overload detection • 80% rule |  | $5,000 breakdown • Contingency • Management Reserve |  | SPI • CPI • EAC • Recovery Plan • Stakeholder Memo
📢 STAKEHOLDER RECOVERY STATEMENT — Week 7 Action Plan
Our Week 6 performance data shows an SPI of 0.80 and a CPI of 0.86, meaning we completed only 80% of the planned work while spending more than budgeted — primarily due to the 3-day delay in Task 6.1 (Module 4 Design) and Sarah's overallocation causing quality rework costs. In Week 7, we will: (1) reassign the non-critical Student Handbook task from Sarah to Layla to immediately reduce her workload from 38 hrs to 30 hrs/week; (2) implement daily 15-min stand-ups to surface blockers early; and (3) freeze any scope additions until CPI returns above 0.95. Our $750 Contingency Reserve remains intact and untouched.
Most2baly Youth Bootcamp • PM Course — Week 6 Milestone • Prepared by: Project Manager • Date: Week 6
📌 Most2baly Youth Bootcamp • PM Course — Week 6 Milestone • Resource Planning & Budget Management • EVM Analysis

## 📊 Resource Matrix
📊 RESOURCE UTILIZATION MATRIX ¦ 80% CAPACITY RULE ENFORCED
🟢 GREEN = ≤ 30 hrs (SAFE — 80% utilization) 🟡 AMBER = 31–37 hrs (WARNING — approaching limit) 🔴 RED = ≥ 38 hrs (OVERLOADED — action required) 📌 Max ideal = 30 hrs/week
Team Member | Assigned Task(s) | Role | Wk4 Hrs | Wk5 Hrs | Wk6 Hrs (ACTUAL) | Status | Ideal Max (30h) | Action Required
Sarah Al-Hassan | Module 4 Design ⚡ + Student Handbook | Lead Designer | 28 | 31 | 38 | 🔴 OVERLOADED | 30 | REASSIGN non-critical task immediately
Ahmed Karim | Module 4 Recording + Backend Setup | Content Producer | 25 | 27 | 26 | ✅ SAFE | 30 | No action needed
Nour Ibrahim | Speaker Logistics + Marketing | Events Coordinator | 22 | 24 | 29 | ✅ SAFE | 30 | No action needed
Mahmoud Fathi | Tech Support + Platform QA | Tech Lead | 20 | 22 | 21 | ✅ SAFE | 30 | No action needed
Layla Mostafa | Student Communication + Handbook | Student Success Mgr | 18 | 20 | 22 | ✅ SAFE | 30 | No action needed
Omar Sayed | Vendor Mgmt + Procurement | Operations Manager | 24 | 26 | 27 | ✅ SAFE | 30 | No action needed
Hana El-Sayed | Social Media + Content Writing | Marketing Specialist | 20 | 23 | 25 | ✅ SAFE | 30 | No action needed
TEAM AVERAGE (Weekly Hours) |  |  | 22.4 | 24.7 | 26.9 | TEAM AVERAGE | 30 | Target: Keep all ≤ 30 hrs
🔧 RESOURCE LEVELING ACTION PLAN ¦ CRITICAL PATH PROTECTED
🔴 Problem Identified: |  | Sarah Al-Hassan is at 38 hrs/week — 27% OVER the 30-hr safe limit.
Root cause: She is assigned BOTH the Critical Path task (Module 4 Design) AND the non-critical Student Handbook simultaneously.
✅ Leveling Action Applied: |  | REASSIGN 'Student Handbook' (Task 6.2) from Sarah → Ahmed Karim.
Justification: Task 6.2 is NOT a prerequisite for any upcoming tech/marketing tasks (per schedule extract). Layla is at only 22 hrs/week — has 8 hrs of free capacity.
📌 Critical Path Protection: |  | Task 6.1 (Module 4 Design) stays with Sarah — she is the only qualified designer.
After reassignment: Sarah drops from 38 → 30 hrs/week (within 80% rule). Layla increases from 22 → 30 hrs/week (exactly at safe limit).
📅 Timeline Impact: |  | ZERO impact on the critical path. The project end date is fully protected.
Student Handbook (Task 6.2) remains on schedule for its Week 12 deadline, now handled by Layla with proper time available.
📌 Most2baly Youth Bootcamp • PM Course — Week 6 Milestone • Resource Planning & Budget Management • EVM Analysis

## 💰 Budget & Envelopes
💰 THREE-ENVELOPE BUDGET BREAKDOWN ¦ $5,000 TOTAL ¦ MOST2BALY BOOTCAMP
Professional PMs protect their budgets with 3 envelopes: Direct Work + Contingency Reserve (Known Risks) + Management Reserve (Unknown Surprises)
📦 ENVELOPE 1 |  | 🛡️ ENVELOPE 2 |  |  | 🚨 ENVELOPE 3
Planned Work Budget |  | Contingency Reserve (15%) |  |  | Management Reserve (5%)
$4,000 (80% of total) |  | $750 (15% of total) |  |  | $250 (5% of total)
All direct & indirect costs for actual project deliverables and operations. |  | For KNOWN risks already identified in the Risk Register. Approved by PM. |  |  | For UNKNOWN surprises only. Sponsor approval required. CANNOT be used by PM alone.
🎤 Guest Speaker Fees | $600 | 📈 Venue price increase risk |  | $200 | ⚡ Unforeseen emergency costs |  | $250
🏢 Venue & Logistics | $800 | 🎤 Speaker cancellation backup |  | $250 | TOTAL ENVELOPE 3 |  | $250
📚 Student Workbooks (Printing) | $350 | 📦 Material cost overrun |  | $150
🎬 Video Recording & Editing | $700 | 🔧 Tech failure recovery |  | $150
💻 Platform & Tech Setup | $450 | TOTAL ENVELOPE 2 |  | $750
📣 Marketing & Social Media | $300
👩‍💼 Project Management (Labor) | $500
📋 Admin & Miscellaneous | $300
TOTAL ENVELOPE 1 | $4,000
📊 BUDGET SUMMARY — ALL THREE ENVELOPES COMBINED
Budget Category | Amount ($) | % of Total |  |  |  | Notes
Envelope 1 — Planned Work | $4,000 | 80.0% | Core deliverables & operations
Envelope 2 — Contingency | $750 | 15.0% | Known risk buffer — PM approves
Envelope 3 — Mgmt Reserve | $250 | 5.0% | Unknown surprises — SPONSOR approves
TOTAL PROJECT BUDGET | $5,000 | 100%
⚠️ CRITICAL BUDGET RULES — Every PM Must Know
1️⃣ Contingency Reserve ≠ Free Money. It is CONTROLLED risk protection for pre-identified risks only.
2️⃣ Management Reserve is NOT yours to spend. Only the Project Sponsor can authorize it.
3️⃣ NEVER use Contingency for Scope Creep. Scope changes need a formal Change Request.
4️⃣ Current Status: Both reserves are INTACT ($1,000 total). CPI of 0.85 has NOT yet consumed any buffer.
5️⃣ EAC Projection ($2,059 at current CPI) means the $4,000 envelope is at risk if trend continues beyond Week 8.
📌 Most2baly Youth Bootcamp • PM Course — Week 6 Milestone • Resource Planning & Budget Management • EVM Analysis

## 📈 EVM Health Indices
📈 EARNED VALUE MANAGEMENT (EVM) ¦ WEEK 6 HEALTH INDICES ¦ FUEL GAUGE ANALYSIS
🔢 RAW DATA INPUTS (Source: Project Accounting & Time-Tracking System — End of Week 6)
Metric | Value | Definition
Planned Value (PV) | $1,875 | The value of work PLANNED to be done by Week 6. (37% of $5,000 budget)
Earned Value (EV) | $1,500 | The value of work ACTUALLY COMPLETED and verified by Week 6.
Actual Cost (AC) | $1,750 | Total money ACTUALLY SPENT on the project through Week 6.
📐 PERFORMANCE INDICES — CALCULATED RESULTS
Index | Formula | Calculation | Result | Meaning | Status | Interpretation
SV (Schedule Variance) | EV − PV | $1,500 − $1,875 | −$375 | Negative = Behind Schedule | ⚠️ BEHIND | We are $375 worth of work BEHIND where we should be. Task 6.1 delay is the main driver.
CV (Cost Variance) | EV − AC | $1,500 − $1,750 | −$250 | Negative = Over Budget | ⚠️ OVER | We spent $250 MORE than the value of work produced. Rework costs from overloaded team.
SPI (Schedule Index) | EV ÷ PV | $1,500 ÷ $1,875 | 0.80 | < 1.0 = Behind Schedule | ⚠️ 0.80 | For every $1 of planned work, we are only delivering $0.80 worth. 20% behind plan.
CPI (Cost Index) | EV ÷ AC | $1,500 ÷ $1,750 | 0.857 | < 1.0 = Over Budget | ⚠️ 0.86 | For every $1 spent, we only get $0.857 of value back. We are 'leaking' 14.3 cents per dollar.
EAC (Est. at Completion) | BAC ÷ CPI | $5,000 ÷ 0.857 | 5834 | Total cost if trend continues | 🔴 OVER | If CPI stays at 0.857, the project will cost $5,833 — $834 OVER the $5,000 budget!
ETC (Est. to Complete) | EAC − AC | $5,834 − $1,750 | 4084 | Remaining budget needed | 📊 WATCH | We still need $4,084 to finish, but only have $5,000 − $1,750 = $3,250 remaining. Deficit = $834
VAC (Variance at Comp.) | BAC − EAC | $5,000 − $5,834 | −$834 | Projected budget overrun | 🔴 −$834 | We are projected to OVERSPEND by $834 Contingency Reserve ($750) partially covers this.
🔄 WEEK 7 RECOVERY PLAN ¦ FORMAL STAKEHOLDER MEMO
TO: Most2baly Board of Directors ¦ FROM: Project Manager ¦ RE: Week 6 Performance Report & Recovery Actions
📊 Current State (The Numbers):
Our SPI of 0.80 shows we completed only 80% of planned work due to the 3-day delay in Module 4 Design (Task 6.1). Our CPI of 0.857 reflects cost inefficiency caused by rework from our overloaded Lead Designer (38 hrs/week).
🔧 Root Cause Analysis:
Single point of failure: Sarah Al-Hassan was assigned both the critical design task AND the Student Handbook simultaneously. This caused quality drops, rework, and slower progress — spending money without proportional value delivery.
✅ Week 7 Actions (Specific & Committed):
1) REASSIGN Student Handbook from Sarah → Layla (frees 8 hrs for Sarah, stays within critical path). 2) Daily 15-min blockers stand-up starting Monday Week 7. 3) Freeze all new requests — no scope additions until CPI > 0.95. 4) Weekly budget review upgraded from monthly to WEEKLY tracking.
💰 Reserve Status (Good News):
BOTH reserves remain completely untouched: Contingency Reserve ($750) + Management Reserve ($250) = $1,000 buffer. The projected overrun (VAC = −$834) is within the combined reserves. NO budget request is needed at this time. If recovery actions work in Week 7-8, we project CPI returning to 0.95 and staying within the $5,000 envelope.
📈 Confidence Statement:
"We are 37% through the project. Early detection is a strength, not a failure. Professional PMs catch problems at Week 6, not Week 15. Our $1,000 reserve buffer is designed exactly for this scenario. With the leveling action implemented Monday, we project SPI > 0.90 and CPI > 0.90 by end of Week 8." — Project Manager
💡 PRO-HACK — The CPI Dashboard Insight
"A CPI below 1.0 is not just a number — it is an early warning light on your dashboard. It means for every $1 spent, you are getting less than $1 of work value in return. The question professional PMs ask is not 'how much have we spent?' but 'what did we GET for that money?' EV is the only honest answer. Catching a CPI of 0.857 at Week 6 — with 10 weeks remaining and reserves intact — is exactly the right time to act. Waiting until Week 14 would turn a $834 problem into a $3,000 crisis."
📌 Most2baly Youth Bootcamp • PM Course — Week 6 Milestone • Resource Planning & Budget Management • EVM Analysis